## Agile_table (hidden)
At Risk | Task Name | Feature Type | Responsible | Depends On | Start Date | End Date | Duratrion | Status | Main Deliverables
Yes | Sprint 0 – Pre-coding |  |  |  | 2026-10-05 | 2026-10-10
| Confirm requirements, scope and traceability baseline |  |  |  | 2026-10-06 | 2026-10-10 |  |  | Stable requirements, priorities and traceability baseline
| Plan site structure, navigation and main user journey |  |  |  | 2026-10-13 | 2026-10-17 |  |  | Site map and main user journey
| Create wireframes |  |  |  | 2026-10-13 | 2026-10-17 |  |  | Low-fidelity wireframes with accessibility notes
| Create interface style, ERD, data dictionary and system architecture |  |  |  | 2026-10-20 | 2026-10-24 |  |  | UI style guide, ERD, data dictionary, architecture/build sequence
| Sprint 1 – Foundation |  |  |  | 2026-11-02 | 2026-11-02
| Build Flask/Jinja core pages and navigation |  |  |  | 2026-11-03 | 2026-11-10 |  |  | Working base template, routes, navigation and responsive core pages
| Sprint 2 – Catalogue & Data |  |  |  | 2026-11-16 | 2026-11-24
| Build catalogue/game details and connect SQLite |  |  |  | 2026-11-17 | 2026-11-24 |  |  | Catalogue/details driven by database data
| Sprint 3 – Basket |  |  |  | 2026-12-01 | 2026-12-08
| Build basket/order review and quantity validation |  |  |  | 2026-12-02 | 2026-12-08 |  |  | Working basket with add/update/remove and validation
| Sprint 4 – Checkout |  |  |  | 2026-12-14 | 2027-01-05
| Build simulated checkout, save order and confirmation |  |  |  | 2026-12-15 | 2027-01-05 |  |  | End-to-end order journey and stored order data
| Sprint 5 – QA |  |  |  | 2027-01-12 | 2027-01-12
| Test against requirements and acceptance criteria |  |  |  | 2027-01-12 | 2027-01-12 |  |  | Completed test results, defects and evidence
| Sprint 6 – QA |  |  |  | 2027-01-19 | 2027-01-19
| Fix defects, retest and complete final review |  |  |  | 2027-01-20 | 2027-01-19 |  |  | Passed retests, updated evidence and final review
| Release Buffer |  |  |  | 2027-01-21 | 2027-01-26
| Contingency, regression testing and final evidence check |  |  |  | 2027-01-21 | 2027-01-21 |  |  | Release-ready PixelForge project and evidence pack

## Plan
Project Plan
| Project Name: | Café 19 Ordering System | Start Date | End Date | Overall Progress |  | Project Deliverables
| Project Manager: | John Adikwu | 2026-10-06 | 2027-01-21 |  |  | Scope Statement
| At Risk | Task Name | Feature Type | Responsible | Depends On | Start Date | End Date | Duratrion | Status | Main Deliverables
| No | Requirements, scope and traceability | New | System Analyst | Problem Identification | 2026-10-06 | 2026-10-10 | 5 | Not Stated | Stable requirements, priorities and traceability baseline
| No | Site structure, navigation and main user journey | New |  |  | 2026-10-13 | 2026-10-17 | 5 |  | Site map and main user journey
| No | Wireframes |  |  |  | 2026-10-13 | 2026-10-17 | 5 |  | Low-fidelity wireframes with accessibility notes
| No | UI style, ERD, data dictionary and system architecture | New |  |  | 2026-10-20 | 2026-10-24 | 5 |  | UI style guide, ERD, data dictionary, architecture/build sequence
| No | Build Flask/Jinja core pages and navigation | New |  |  | 2026-11-03 | 2026-11-10 | 8 |  | Working base template, routes, navigation and responsive core pages
|  | Catalogue/game details and connect SQLite | New |  |  | 2026-11-17 | 2026-11-24 | 8 |  | Catalogue/details driven by database data
|  | Basket/order review and quantity validation | New |  |  | 2026-12-02 | 2026-12-08 | 7 |  | Working basket with add/update/remove and validation
|  | Simulated checkout, save order and confirmation | New |  |  | 2026-12-15 | 2027-01-05 | 22 |  | End-to-end order journey and stored order data
|  | Test against requirements and acceptance criteria | New |  |  | 2027-01-12 | 2027-01-12 | 1 |  | Completed test results, defects and evidence
|  | Fix defects, retest and complete final review | New |  |  | 2027-01-19 | 2027-01-19 | 1 |  | Passed retests, updated evidence and final review
|  | Contingency, regression testing and final evidence check | New |  |  | 2027-01-21 | 2027-01-21 | 1 |  | Release-ready PixelForge project and evidence pack

## Key
Key
At Risk | Feature Type |  | Status
Yes | New |  | Not Stated
No | Improvement |  | In Progress
| Bug |  | Complete
Need Review
Approved
Over Due
On Hold